## Slide 1
3 Sprint Agile Communications Activities Plan - How to use it
If you’re starting out on your transformation, start with sprint 1.
If you’re already on your transformation, start with sprint 3 and tailor it to where you are on your transformation.
The comms are laid out by week 1 (top) and week 2 (bottom).
All comms are assigned a theme to drive behaviour or an action; functional/tactical; or for learning.
Align to your transformation vision and goals.
Examples included to get you started.
Comms cadence aimed at two audience groups:
  Colleagues going through the transformation, if phased roll out
  The whole org to prime them and take them on the journey.
Learning activities: By Agile maturity: Low – e.g. What is Agile; High - vote on a topic
Adapt to your requirements, channels/media and how your people engage with comms.
Notes: Questions
Where on the vision and goals of the transformation
What needs to happen to get there, the steps
Key milestones
Key achievements to celebrate
Coming up in the next 3 months, and 2 sprint
How are people feeling
Are they aligned
What do you need them to do
Key people to speak to/good news success stories
Design comms plan
Maintain this relationship
NEXT: 3 Sprint Agile Communications Activities Plan - How to use it

## Slide 2
3-Sprint Communications Plans
For Small/Light Scale Agile Transformations

## Slide 3
DAY 1
DAY 2
DAY 3
DAY 4
DAY 5
Week 1
Week 2
Agile Communications Activities Plan© | Sprint 1 Communicating Change
Announcement from Executive/Sponsor1 to the whole org(I)
All Hands1 (I, C, A)
Story2 (L, A)
KEY: Assign a theme to all comms
(I) Inform Important information or actions
(L) Learn Learn & knowledge share, L&L, Lean Coffees etc
(C) Culture Influence culture and hearts & minds
(A) Action Drive actions and behaviour changes
Examples
The upcoming Agile transformation & its importance; The Why, The Vision; Q&As
The Need for Change

## Slide 4
DAY 1
DAY 2
DAY 3
DAY 4
DAY 5
Week 1
Week 2
Agile Communications Activities Plan© | Sprint 2
Transformation Update2 for colleagues on the journey (I, C ,A)
KEY: Assign a theme to all comms
(I) Inform Important information or actions
(L) Learn Learn & knowledge share, L&L, Lean Coffees etc
(C) Culture Influence culture and hearts & minds
(A) Action Drive actions and behaviour changes
Examples
New go-to place for all things Agile; info & support, Q&As
Update on the Agile Transformation; Next steps/Key focus, Q&A
Navigating Change
Launch of dedicated website1 (L)
Story3 (L, A)

## Slide 5
DAY 1
DAY 2
DAY 3
DAY 4
DAY 5
Week 1
Week 2
Agile Communications Activities Plan© | Sprint 3
Colleague interview1 (C)
Lunch & Learn/Lean Coffee4 (L, C)
KEY: Assign a theme to all comms
(I) Inform Important information or actions
(L) Learn Learn & knowledge share, L&L, Lean Coffees etc
(C) Culture Influence culture and hearts & minds
(A) Action Drive actions and behaviour changes
Examples
Inspiring blog about their role, e.g. Architect, Scrum Master
Ways of Working/success/themed stories
Update on the Agile Transformation; Next steps/Key focus, Q&A
Learning & knowledge sharing session
Round up of all the news
Story2 (L, C, A)
Newsletter5 (I,L,C,A)
Executive/Sponsor Update to the whole org3 (C)

## Slide 6
3-Sprint Communications Plans
For a Large Scale Agile Transformation

## Slide 7
DAY 1
DAY 2
DAY 3
DAY 4
DAY 5
Week 1
Week 2
Agile Communications Activities Plan© | Sprint 1 Communicating Change
Announcement from Executive/Sponsor1 to the whole org(I)
KEY: Assign a theme to all comms
(I) Inform Important information or actions
(L) Learn Learn & knowledge share, L&L, Lean Coffees etc
(C) Culture Influence culture and hearts & minds
(A) Action Drive actions and behaviour changes
Examples
The upcoming Agile transformation & its importance; The Why, The Vision; Q&As (Impacted/all colleagues)
The Need for Change
Story2 (L, C, A)
All Hands1 with the whole org (I, C, A)
Leadership Team Stand up1 with colleagues going thro’ the transformation (I, C, A)

## Slide 8
DAY 1
DAY 2
DAY 3
DAY 4
DAY 5
Week 1
Week 2
Agile Communications Activities Plan© | Sprint 2
Leadership Team Stand up1 with colleagues going thro’ the transformation (I, C, A)
Lunch & Learn/Lean Coffee4
KEY: Assign a theme to all comms
(I) Inform Important information or actions
(L) Learn Learn & knowledge share, L&L, Lean Coffees etc
(C) Culture Influence culture and hearts & minds
(A) Action Drive actions and behaviour changes
Examples
Update on the Agile Transformation; Next steps/Key focus, Q&A
New go-to place for all things Agile; info & support, Q&As
Ways of Working/success/themed stories
Learning & knowledge sharing session
Story3 (L, C, A)
Launch of dedicated website2 (L)

## Slide 9
DAY 1
DAY 2
DAY 3
DAY 4
DAY 5
Week 1
Week 2
Agile Communications Activities Plan© | Sprint 3
Colleague interview1 (C)
Executive/Sponsor Checkpoint4 (C, A)
Lunch & Learn/Lean Coffee5
KEY: Assign a theme to all comms
(I) Inform Important information or actions
(L) Learn Learn & knowledge share, L&L, Lean Coffees etc
(C) Culture Influence culture and hearts & minds
(A) Action Drive actions and behaviour changes
Examples
Inspiring blog about their role, e.g. Architect, Scrum Master
Update on the Agile Transformation: Next steps/Key focus, Q&A (Impacted/all colleagues)
Ways of Working/success/themed stories
Sponsor check-in
Learning & knowledge sharing session
Round up of all the news
Story3 (L, C, A)
Transformation Update2 for all colleagues (I, C ,A)
Colleague interview1 (C)
Story3 (L, C, A)
Newsletter6 (I,L,C,A)
Leadership Team Stand up2 with colleagues going thro’ the transformation (I, C, A)